## Sheet1
PROCUREMENT PLAN FOR GOODS,WORKS AND NON CONSULTANCY SERVICES - EXTERNAL USE
Name of Procuring Entity - AE/ 034 - Dodoma Urban Water Supply and Sanitation Authority
FINANCIAL YEAR - 2019/2020
S/N | Descriptions | Tender No. | Lot number | Procurement Method | Estimated Amount in Tshs | Basic Data |  | Gen. Proc Notice Advert | PRE - QUALIFICATION |  |  |  | Invitation for Tenders and Contract Signature
[6 empty] | Selection Method | Contract Type |  | Invitation Date | Closing-Opening | Approval of Shortlist | Notification of applicants | Tender Invitation Date | Tenders closing/Opening Opening Date | Notice of intetion to award | Vetting/Ratification of Contract | Notification of Award | Plan V/S Actual date of implementation
| 1 | 2 | 3 | 4 |  |  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
GOODS
1 | The supply of water treatment Chemical, Labaratory Reagents and Equipments | AE/034/HQ/2019-2020/G/01 |  | NCT | 158200000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
2 | The supply of 500 Pre paid water meter and 2000 Lockable Valve for new connections and Replacement | AE/034/HQ/2019-2020/G/02 |  | SS | 200000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
3 | The supply of Pipes and Fittings (PVCs, Polyethylene and GS) for Maintanence, New connection and Projects | AE/034/HQ/2019-2020/G/03 | LOT 1 - (PVCs and Polyethylene) | DIRECT/MANUFACTURER | 2722526863.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
|  |  | LOT 2 -(Galvanized and Steel) | NCT | 1170697128.8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
4 | The Supply of Spare Parts and Lubricants for Vehicles, plants, machinery, generator and motorcycles | AE/034/HQ/2019-2020/G/04 |  | FWA/GPSA | 141170000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
5 | The Supply of Spare Parts for Motorcycles | AE/034/HQ/2019-2020/G/05 |  | FWA/GPSA | 18750000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
6 | The Supply of Stationery and Printing Services | AE/034/HQ/2019-2020/G/06 |  | FWA/GPSA | 120000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
7 | The Supply of Computer's consumable Software , Mobile phone and Photocopier Maintanance | AE/034/HQ/2019-2020/G/07 |  | FWA/GPSA | 70645000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
8 | The supply of Staff Uniforms ( 210 staff) | AE/034/HQ/2019-2020/G/08 |  | FWA/GPSA | 63000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
9 | The supply of Fuel for vehicles, Plant, Pumps, generator and motorcycles | AE/034/HQ/2019-2020/G/09 |  | SS/GPSA | 259004000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
10 | The Supply of Building Materials, Machinery, Pumps spare parts, site tools and office hardwares | AE/034/HQ/2019-2020/G/10 |  | FWA/GPSA | 357478002 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
11 | The supply of Office Calendars , Diaries (Pocket and executive) year 2020, wheel covers, DUWASA sickers Customer charter and Annual report and Duwasa Pen | AE/034/HQ/2019-2020/G/11 |  | CQ | 45500000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10/09/19 | 18/09/19 | 26/09/19 | 03/10/19 | 15/10/19 | Plan
Actual
12 | The Supply of One (01) Surface pump (545m3/hr) and One (01) Submersible pumps (150m3/hr) and its accessories for Mzakwe pump station | AE/034/HQ/2019-2020/G/12 |  | NCT | 300000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
13 | The Supply and Installation of Solar system at C3 Borehole at Mzakwe Pump station | AE/034/HQ/2019-2020/G/13 |  | NCT | 255599140 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20/11/19 | 6/12/19 | 16/12/19 | 23/12/19 | 31/12/19 | Plan
Actual
14 | The Supply of Motor cycles (Boxer) and Helmets | AE/034/HQ/2019-2020/G/14 |  | SS | 28000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
15 | The Supply of office furnitures and Equipments | AE/034/HQ/2019-2020/G/15 |  | FWA/GPSA | 44075000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
16 | Supply and installation of Centralization system for Operations of Boreholes at Ihumwa Pump Station | AE/034/HQ/2019-2020/G/16 |  | NCT | 200000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20/11/19 | 6/12/19 | 16/12/19 | 23/12/19 | 31/12/19 | Plan
| NON CONSULTANCY | [7 empty] | 14: Actual
17 | Provision of Fumigation and Fire Extinguishers Services | AE/034/HQ/2019-2020/NC/01 |  | FWA/GPSA | 29905000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
18 | Provision of Air Conditioners service and Maintanance | AE/034/HQ/2019-2020/NC/02 |  | FWA/GPSA | 15900000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
19 | Provision of Insurance of Vehicles and Motorcycles | AE/034/HQ/2019-2020/NC/03 |  | SS | 50000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
20 | Provision of office and Surrounding Cleanness Services and maintanance at Makole round about, Mzakwe, Kilimani and Mailimbili booster | AE/034/HQ/2019-2020/NC/04 |  | FWA/GPSA | 85200000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
21 | The Provision of Security Services | AE/034/HQ/2019-2020/NC/05 | LOT 1- SUMAJKT - Ofisi kuu , boosters and tanks | SS | 247800000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
|  |  | LOT 2 - Mzakwe, kilimani, msalato, filter | FWA/GPSA | 225600000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
WORKS
22 | Trench Excavation and backfilling for New connection customers | AE/034/HQ/2019-2020/W/0I |  | CQ | 200000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
23 | Trench Excavation and backfilling for extension of Water Distribution System (Water supply and Sewerage projects) | AE/034/HQ/2019-2020/W/02 |  | RT | 457378064 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2/9/19 | 6/9/19 | 19/9/19 | 26/9/19 | 30/9/19 | Plan
Actual
24 | Repair work of leaking Pipes at Dodoma City | AE/034/HQ/2019-2020/W/03 |  | SS/ SG | 160160000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
25 | Construction of NEW Building for DUWASA office | AE/034/HQ/2019-2020/W/04 |  | SS | 1000000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
26 | Geophysical Survey and Drilling of boreholes at Nala and Ihumwa | AE/034/HQ/2019-2020/W/05 |  | SS | 500000000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/06/19 | 17/06/19 | 24/06/19 | 2/07/19 | 5/07/19 | Plan
Actual
| TOTAL |  |  |  | 9126588198